## README
Laptop Refresh Rollout Tracker (IT Project)
Built by Adam J. Asifo (Claude by Anthropic assisted with formulas and testing) · adamjasifo@gmail.com
What this is
The tracker an IT project coordinator runs to replace 96 old Windows 10 laptops with Windows 11 laptops in 3 waves, without losing anyone's files or leaving old laptops lying around. One row per laptop.
Why build it this way: with 96 people, 'is this person ready?' and 'is this laptop really done?' have to be answered the same way every time, so those rules are built in.
Start here: you only need these 4 things
Don't get overwhelmed. Most of this file fills itself in. These are the only places you type or pick something; everything else updates on its own.
Where | What you do | What happens
Rollout_Dashboard → cell C4 (Status date) | Type a date. | Every count, flag and wave gate re-checks as of that day.
Device_Tracker → column J (Status) | Pick the laptop's step: Scheduled, Imaged, Delivered, Data Migrated, Signed Off or Blocked. | Progress, the daily chart and the Dashboard update. Blocked laptops are flagged.
Device_Tracker → columns L to P | When a laptop is signed off, type the date (L), then pick Y or N for: BitLocker on, old laptop returned, old laptop wiped, asset record updated. | A laptop counts as compliant only when all four are Y. If the old laptop isn't back in 3 days, it's flagged 'Chase old laptop'.
Issue_Log → column H (Status) | Pick Open or Resolved, and type the Resolved Date. | An open Sev1 (blocker) issue stops the next wave. Resolving it clears that part of the gate.
Yellow cells = you type or pick from a list. Cells with a small arrow have a drop-down menu: click the cell, then the arrow, and pick a word. White cells are formulas, so leave them alone.
What each tab is for
Rollout_Dashboard | One page: overall color and why, signed off vs. plan, blocked laptops, open issues, wave gates.
Device_Tracker | One row per laptop: who, which wave, readiness (backup + MFA), status, security checks and flags.
Wave_Plan | GO or NO-GO for each wave, with the reason written in plain English.
Issue_Log | Problems found during the rollout, with severity, owner and a target date.
Daily_Log | Laptops planned vs. signed off each day, with a chart, so a slip shows up the same day.
Comms_Plan | When each user email goes out and who sends it.
Lists | The choices in every drop-down.
Try it (1 minute)
1. Go to Issue_Log. For ISS-03, change Status (column H) to Resolved and type 10/30/2026 in Resolved Date (column I).
2. On the Dashboard, open Sev1 issues drop to 0.
3. On Wave_Plan, Wave 3's reason no longer mentions a Sev1 issue. It's still NO-GO because Wave 2 is only 35% done and only 41% of Wave 3's users are ready.
To undo, press Ctrl+Z (Cmd+Z on a Mac).
Good to know
• Blank on purpose: columns L to P stay empty until a laptop is signed off, Resolved Date stays empty while an issue is open, and Blocker / Note is only filled in when there's a problem.
• Ready = backup confirmed AND MFA (multi-factor sign-in) set up. Nobody gets a new laptop without both.
• To add a laptop or an issue, type on the next empty row. The formulas are already there.
• Works in Excel 2010 or newer (Windows or Mac), Excel online and Google Sheets. Formulas only, no macros, so no security warnings.
• All companies, people, dates and dollar amounts are fictional sample data.

## Rollout_Dashboard
Laptop Refresh Rollout — Dashboard
Sample IT project with fictional data: 96 aging Windows 10 laptops replaced with Windows 11 laptops in 3 waves. Everything here is calculated.
| Status date | 2026-10-30
| OVERALL HEALTH |  |  | Laptops signed off |  | Planned by status date |  | % complete |  | Ahead / (behind) plan
| Amber |  |  | 26 |  | 32 |  | 27.08% |  | -6
Red = more than 10 laptops behind plan, or a Sev1 issue open 4+ days. Amber = behind plan at all, any Sev1 open, or any laptop blocked. Otherwise Green.
|  |  |  | Blocked laptops |  | Open issues (Sev1 / all) |  | Old laptops not returned |  | Signed-off laptops compliant
|  |  |  | 4 |  | 1 / 2 |  | 6 |  | 65.38%
Why this color?
| Laptops behind plan | 6
| Sev1 open 4+ days | 0
| Sev1 open (any age) | 1
| Laptops blocked | 4
Waves
| Wave | Who |  | Start | Laptops | Signed Off | % Done | Users Ready | Gate | Why
| Wave 1 | Pilot: Finance & HR |  | 2026-10-19 | 12 | 12 | 100% | 100% | Complete | All laptops signed off
| Wave 2 | Operations |  | 2026-10-26 | 40 | 14 | 35% | 100% | In progress | Started Oct 26; 14 of 40 signed off
| Wave 3 | Sales & Client Services |  | 2026-11-09 | 44 | 0 | 0% | 40.91% | NO-GO | Prior wave 35% done (need 95%). 1 Sev1 issue open. Users ready 41% (need 95%).
| Why laptops aren't done yet |  |  |  |  | Open issues
| Flag |  | Laptops |  |  | ID | Severity | Description |  |  | Days Open
| Blocked |  | 4 |  |  | ISS-03 | Sev1 - Blocker | Dispatch scheduling app won't activate its license on new laptops; 3 users kept on old laptops |  |  | 3
| Overdue |  | 0 |  |  | ISS-04 | Sev2 - Major | One new laptop arrived with a dead screen; replacement ordered from the reseller |  |  | 2
| Chase old laptop |  | 3 |  |  | —
Note on C4: Change this date to re-run every calculation as of that day. Type =TODAY() for live use.

## Device_Tracker
Device Tracker — One Row per Laptop
Update Status as each swap moves along. Flags, readiness and compliance are automatic. Employee IDs only; no names.
Yellow cells = you type or pick from a list here. White cells fill themselves in (don't type over them).
New Asset Tag | Serial # | Employee ID | Department | Wave | Old Asset Tag | Scheduled Date | Backup Confirmed? | MFA Enrolled? | Status | Blocker / Note | Signed-Off Date | BitLocker On? | Old Laptop Returned? | Old Laptop Wiped? | Asset Record Updated? | User Ready? | Compliant? | Flag
NB-26-001 | 5CG4960229 | E1100 | Finance | Wave 1 | LT-19-410 | 2026-10-19 | Y | Y | Signed Off |  | 2026-10-19 | Y | Y | Y | Y | Ready | Yes |  | Wave 1
NB-26-002 | 5CG2730838 | E1103 | Finance | Wave 1 | LT-19-838 | 2026-10-19 | Y | Y | Signed Off |  | 2026-10-19 | Y | Y | N | Y | Ready | No |  | Wave 1
NB-26-003 | 5CG7644754 | E1106 | Finance | Wave 1 | LT-19-590 | 2026-10-19 | Y | Y | Signed Off |  | 2026-10-19 | Y | Y | Y | Y | Ready | Yes |  | Wave 1
NB-26-004 | 5CG3600003 | E1109 | Finance | Wave 1 | LT-19-192 | 2026-10-19 | Y | Y | Signed Off |  | 2026-10-19 | Y | N | N | Y | Ready | No | Chase old laptop | Wave 1
NB-26-005 | 5CG2115938 | E1112 | Finance | Wave 1 | LT-19-120 | 2026-10-19 | Y | Y | Signed Off |  | 2026-10-19 | Y | Y | Y | N | Ready | No |  | Wave 1
NB-26-006 | 5CG7737579 | E1115 | Finance | Wave 1 | LT-19-662 | 2026-10-19 | Y | Y | Signed Off |  | 2026-10-19 | Y | Y | Y | Y | Ready | Yes |  | Wave 1
NB-26-007 | 5CG5854919 | E1118 | Finance | Wave 1 | LT-19-883 | 2026-10-20 | Y | Y | Signed Off |  | 2026-10-20 | Y | Y | Y | Y | Ready | Yes |  |  | Wave 1
NB-26-008 | 5CG1987289 | E1121 | HR | Wave 1 | LT-19-327 | 2026-10-20 | Y | Y | Signed Off |  | 2026-10-20 | Y | Y | Y | Y | Ready | Yes |  |  | Wave 1
NB-26-009 | 5CG9729844 | E1124 | HR | Wave 1 | LT-19-649 | 2026-10-20 | Y | Y | Signed Off |  | 2026-10-20 | Y | N | N | Y | Ready | No | Chase old laptop |  | Wave 1
NB-26-010 | 5CG7043906 | E1127 | HR | Wave 1 | LT-19-383 | 2026-10-20 | Y | Y | Signed Off |  | 2026-10-20 | Y | Y | Y | Y | Ready | Yes |  |  | Wave 1
NB-26-011 | 5CG3896830 | E1130 | HR | Wave 1 | LT-19-208 | 2026-10-20 | Y | Y | Signed Off |  | 2026-10-20 | Y | Y | Y | Y | Ready | Yes |  |  | Wave 1
NB-26-012 | 5CG5390925 | E1133 | HR | Wave 1 | LT-19-319 | 2026-10-20 | Y | Y | Signed Off |  | 2026-10-20 | Y | Y | Y | Y | Ready | Yes |  |  | Wave 1
NB-26-013 | 5CG1430162 | E1136 | Operations | Wave 2 | LT-19-756 | 2026-10-26 | Y | Y | Signed Off |  | 2026-10-26 | Y | Y | Y | Y | Ready | Yes |  | Wave 2
NB-26-014 | 5CG5366340 | E1139 | Operations | Wave 2 | LT-19-378 | 2026-10-26 | Y | Y | Signed Off |  | 2026-10-26 | Y | Y | Y | Y | Ready | Yes |  | Wave 2
NB-26-015 | 5CG4245311 | E1142 | Operations | Wave 2 | LT-19-268 | 2026-10-26 | Y | Y | Signed Off |  | 2026-10-26 | Y | N | N | Y | Ready | No | Chase old laptop | Wave 2
NB-26-016 | 5CG6198419 | E1145 | Operations | Wave 2 | LT-19-396 | 2026-10-26 | Y | Y | Signed Off |  | 2026-10-26 | Y | Y | Y | Y | Ready | Yes |  | Wave 2
NB-26-017 | 5CG7247719 | E1148 | Operations | Wave 2 | LT-19-188 | 2026-10-27 | Y | Y | Signed Off |  | 2026-10-27 | Y | Y | N | Y | Ready | No
NB-26-018 | 5CG6660674 | E1151 | Operations | Wave 2 | LT-19-787 | 2026-10-27 | Y | Y | Blocked | Dispatch app license won't activate (ISS-03); user kept on old laptop | [5 empty] | Ready |  | Blocked
NB-26-019 | 5CG7508416 | E1154 | Operations | Wave 2 | LT-19-618 | 2026-10-27 | Y | Y | Blocked | Dispatch app license won't activate (ISS-03); user kept on old laptop | [5 empty] | Ready |  | Blocked
NB-26-020 | 5CG5175405 | E1157 | Operations | Wave 2 | LT-19-282 | 2026-10-27 | Y | Y | Blocked | Dispatch app license won't activate (ISS-03); user kept on old laptop | [5 empty] | Ready |  | Blocked
NB-26-021 | 5CG5149378 | E1160 | Operations | Wave 2 | LT-19-584 | 2026-10-28 | Y | Y | Signed Off |  | 2026-10-28 | Y | Y | Y | Y | Ready | Yes
NB-26-022 | 5CG5697580 | E1163 | Operations | Wave 2 | LT-19-191 | 2026-10-28 | Y | Y | Signed Off |  | 2026-10-28 | Y | Y | Y | Y | Ready | Yes
NB-26-023 | 5CG6037287 | E1166 | Operations | Wave 2 | LT-19-107 | 2026-10-28 | Y | Y | Blocked | New laptop arrived with dead screen; replacement ordered (ISS-04) | [5 empty] | Ready |  | Blocked
NB-26-024 | 5CG5897968 | E1169 | Operations | Wave 2 | LT-19-686 | 2026-10-28 | Y | Y | Signed Off |  | 2026-10-28 | Y | Y | Y | Y | Ready | Yes
NB-26-025 | 5CG6230501 | E1172 | Operations | Wave 2 | LT-19-883 | 2026-10-29 | Y | Y | Signed Off |  | 2026-10-29 | Y | Y | Y | Y | Ready | Yes
NB-26-026 | 5CG9529073 | E1175 | Operations | Wave 2 | LT-19-299 | 2026-10-29 | Y | Y | Signed Off |  | 2026-10-29 | Y | N | N | N | Ready | No
NB-26-027 | 5CG7944862 | E1178 | Operations | Wave 2 | LT-19-533 | 2026-10-29 | Y | Y | Signed Off |  | 2026-10-29 | Y | Y | Y | Y | Ready | Yes
NB-26-028 | 5CG5835253 | E1181 | Operations | Wave 2 | LT-19-541 | 2026-10-29 | Y | Y | Signed Off |  | 2026-10-29 | Y | N | N | Y | Ready | No
NB-26-029 | 5CG8572772 | E1184 | Operations | Wave 2 | LT-19-265 | 2026-10-30 | Y | Y | Signed Off |  | 2026-10-30 | Y | Y | Y | Y | Ready | Yes
NB-26-030 | 5CG4912869 | E1187 | Operations | Wave 2 | LT-19-412 | 2026-10-30 | Y | Y | Signed Off |  | 2026-10-30 | Y | N | N | Y | Ready | No
NB-26-031 | 5CG5356290 | E1190 | Operations | Wave 2 | LT-19-144 | 2026-10-30 | Y | Y | Data Migrated | Waiting on user sign-off | [5 empty] | Ready
NB-26-032 | 5CG2360220 | E1193 | Operations | Wave 2 | LT-19-147 | 2026-10-30 | Y | Y | Delivered | OneDrive sync in progress | [5 empty] | Ready
NB-26-033 | 5CG8762310 | E1196 | Operations | Wave 2 | LT-19-741 | 2026-11-02 | Y | Y | Imaged | [6 empty] | Ready
NB-26-034 | 5CG5704888 | E1199 | Operations | Wave 2 | LT-19-631 | 2026-11-02 | Y | Y | Imaged | [6 empty] | Ready
NB-26-035 | 5CG9969465 | E1202 | Operations | Wave 2 | LT-19-763 | 2026-11-02 | Y | Y | Imaged | [6 empty] | Ready
NB-26-036 | 5CG8906096 | E1205 | Operations | Wave 2 | LT-19-817 | 2026-11-02 | Y | Y | Imaged | [6 empty] | Ready
NB-26-037 | 5CG6751955 | E1208 | Operations | Wave 2 | LT-19-248 | 2026-11-03 | Y | Y | Imaged | [6 empty] | Ready
NB-26-038 | 5CG4281178 | E1211 | Operations | Wave 2 | LT-19-168 | 2026-11-03 | Y | Y | Imaged | [6 empty] | Ready
NB-26-039 | 5CG7925545 | E1214 | Operations | Wave 2 | LT-19-307 | 2026-11-03 | Y | Y | Imaged | [6 empty] | Ready
NB-26-040 | 5CG8401301 | E1217 | Operations | Wave 2 | LT-19-382 | 2026-11-03 | Y | Y | Imaged | [6 empty] | Ready
NB-26-041 | 5CG4082035 | E1220 | Operations | Wave 2 | LT-19-464 | 2026-11-04 | Y | Y | Scheduled | [6 empty] | Ready
NB-26-042 | 5CG8313596 | E1223 | Operations | Wave 2 | LT-19-864 | 2026-11-04 | Y | Y | Scheduled | [6 empty] | Ready
NB-26-043 | 5CG6379931 | E1226 | Operations | Wave 2 | LT-19-749 | 2026-11-04 | Y | Y | Scheduled | [6 empty] | Ready
NB-26-044 | 5CG4333837 | E1229 | Operations | Wave 2 | LT-19-431 | 2026-11-04 | Y | Y | Scheduled | [6 empty] | Ready
NB-26-045 | 5CG2694153 | E1232 | Operations | Wave 2 | LT-19-163 | 2026-11-05 | Y | Y | Scheduled | [6 empty] | Ready
NB-26-046 | 5CG4839792 | E1235 | Operations | Wave 2 | LT-19-384 | 2026-11-05 | Y | Y | Scheduled | [6 empty] | Ready
NB-26-047 | 5CG4983199 | E1238 | Operations | Wave 2 | LT-19-225 | 2026-11-05 | Y | Y | Scheduled | [6 empty] | Ready
NB-26-048 | 5CG6554382 | E1241 | Operations | Wave 2 | LT-19-281 | 2026-11-05 | Y | Y | Scheduled | [6 empty] | Ready
NB-26-049 | 5CG5880899 | E1244 | Operations | Wave 2 | LT-19-570 | 2026-11-06 | Y | Y | Scheduled | [6 empty] | Ready |  |  |  | Wave 2
NB-26-050 | 5CG1430773 | E1247 | Operations | Wave 2 | LT-19-143 | 2026-11-06 | Y | Y | Scheduled | [6 empty] | Ready |  |  |  | Wave 2
NB-26-051 | 5CG6990876 | E1250 | Operations | Wave 2 | LT-19-814 | 2026-11-06 | Y | Y | Scheduled | [6 empty] | Ready |  |  |  | Wave 2
NB-26-052 | 5CG2385971 | E1253 | Operations | Wave 2 | LT-19-392 | 2026-11-06 | Y | Y | Scheduled | [6 empty] | Ready |  |  |  | Wave 2
NB-26-053 | 5CG6488199 | E1256 | Sales | Wave 3 | LT-19-118 | 2026-11-09 | Y | Y | Scheduled | [6 empty] | Ready |  |  | Wave 3
NB-26-054 | 5CG6415857 | E1259 | Sales | Wave 3 | LT-19-395 | 2026-11-09 | N | Y | Scheduled | [6 empty] | Not ready |  |  | Wave 3
NB-26-055 | 5CG6396829 | E1262 | Sales | Wave 3 | LT-19-256 | 2026-11-09 | Y | N | Scheduled | [6 empty] | Not ready |  |  | Wave 3
NB-26-056 | 5CG7885833 | E1265 | Sales | Wave 3 | LT-19-735 | 2026-11-09 | Y | Y | Scheduled | [6 empty] | Ready |  |  | Wave 3
NB-26-057 | 5CG2304534 | E1268 | Sales | Wave 3 | LT-19-400 | 2026-11-09 | Y | Y | Scheduled | [6 empty] | Ready |  |  | Wave 3
NB-26-058 | 5CG4211414 | E1271 | Sales | Wave 3 | LT-19-554 | 2026-11-10 | N | Y | Scheduled | [6 empty] | Not ready
NB-26-059 | 5CG5898868 | E1274 | Sales | Wave 3 | LT-19-239 | 2026-11-10 | Y | N | Scheduled | [6 empty] | Not ready
NB-26-060 | 5CG5195098 | E1277 | Sales | Wave 3 | LT-19-490 | 2026-11-10 | N | Y | Scheduled | [6 empty] | Not ready
NB-26-061 | 5CG3665977 | E1280 | Sales | Wave 3 | LT-19-439 | 2026-11-10 | Y | Y | Scheduled | [6 empty] | Ready
NB-26-062 | 5CG1157646 | E1283 | Sales | Wave 3 | LT-19-472 | 2026-11-10 | N | Y | Scheduled | [6 empty] | Not ready
NB-26-063 | 5CG1751572 | E1286 | Sales | Wave 3 | LT-19-565 | 2026-11-11 | Y | Y | Scheduled | [6 empty] | Ready
NB-26-064 | 5CG3844862 | E1289 | Sales | Wave 3 | LT-19-473 | 2026-11-11 | N | N | Scheduled | [6 empty] | Not ready
NB-26-065 | 5CG7085503 | E1292 | Sales | Wave 3 | LT-19-397 | 2026-11-11 | Y | Y | Scheduled | [6 empty] | Ready
NB-26-066 | 5CG2629104 | E1295 | Sales | Wave 3 | LT-19-549 | 2026-11-11 | N | Y | Scheduled | [6 empty] | Not ready
NB-26-067 | 5CG4476855 | E1298 | Sales | Wave 3 | LT-19-534 | 2026-11-11 | Y | Y | Scheduled | [6 empty] | Ready
NB-26-068 | 5CG4488265 | E1301 | Sales | Wave 3 | LT-19-216 | 2026-11-12 | N | N | Scheduled | [6 empty] | Not ready
NB-26-069 | 5CG1995552 | E1304 | Sales | Wave 3 | LT-19-163 | 2026-11-12 | Y | Y | Scheduled | [6 empty] | Ready
NB-26-070 | 5CG1927287 | E1307 | Sales | Wave 3 | LT-19-854 | 2026-11-12 | Y | Y | Scheduled | [6 empty] | Ready
NB-26-071 | 5CG3829817 | E1310 | Sales | Wave 3 | LT-19-709 | 2026-11-12 | Y | Y | Scheduled | [6 empty] | Ready
NB-26-072 | 5CG3510551 | E1313 | Sales | Wave 3 | LT-19-721 | 2026-11-12 | N | Y | Scheduled | [6 empty] | Not ready
NB-26-073 | 5CG1686060 | E1316 | Sales | Wave 3 | LT-19-659 | 2026-11-13 | Y | N | Scheduled | [6 empty] | Not ready
NB-26-074 | 5CG9232036 | E1319 | Sales | Wave 3 | LT-19-696 | 2026-11-13 | N | Y | Scheduled | [6 empty] | Not ready
NB-26-075 | 5CG5178510 | E1322 | Sales | Wave 3 | LT-19-429 | 2026-11-13 | Y | Y | Scheduled | [6 empty] | Ready
NB-26-076 | 5CG1596831 | E1325 | Sales | Wave 3 | LT-19-225 | 2026-11-13 | N | Y | Scheduled | [6 empty] | Not ready
NB-26-077 | 5CG9879200 | E1328 | Sales | Wave 3 | LT-19-399 | 2026-11-16 | Y | N | Scheduled | [6 empty] | Not ready
NB-26-078 | 5CG7867270 | E1331 | Sales | Wave 3 | LT-19-767 | 2026-11-16 | N | Y | Scheduled | [6 empty] | Not ready
NB-26-079 | 5CG4359829 | E1334 | Client Services | Wave 3 | LT-19-589 | 2026-11-16 | Y | Y | Scheduled | [6 empty] | Ready
NB-26-080 | 5CG4385184 | E1337 | Client Services | Wave 3 | LT-19-347 | 2026-11-16 | N | Y | Scheduled | [6 empty] | Not ready
NB-26-081 | 5CG8362080 | E1340 | Client Services | Wave 3 | LT-19-520 | 2026-11-17 | Y | Y | Scheduled | [6 empty] | Ready
NB-26-082 | 5CG9253361 | E1343 | Client Services | Wave 3 | LT-19-137 | 2026-11-17 | N | N | Scheduled | [6 empty] | Not ready
NB-26-083 | 5CG4675242 | E1346 | Client Services | Wave 3 | LT-19-531 | 2026-11-17 | Y | Y | Scheduled | [6 empty] | Ready
NB-26-084 | 5CG8440730 | E1349 | Client Services | Wave 3 | LT-19-354 | 2026-11-17 | Y | Y | Scheduled | [6 empty] | Ready
NB-26-085 | 5CG8177912 | E1352 | Client Services | Wave 3 | LT-19-320 | 2026-11-18 | Y | Y | Scheduled | [6 empty] | Ready
NB-26-086 | 5CG9364779 | E1355 | Client Services | Wave 3 | LT-19-292 | 2026-11-18 | N | N | Scheduled | [6 empty] | Not ready
NB-26-087 | 5CG1531004 | E1358 | Client Services | Wave 3 | LT-19-137 | 2026-11-18 | Y | Y | Scheduled | [6 empty] | Ready
NB-26-088 | 5CG5268017 | E1361 | Client Services | Wave 3 | LT-19-359 | 2026-11-18 | N | Y | Scheduled | [6 empty] | Not ready
NB-26-089 | 5CG5066614 | E1364 | Client Services | Wave 3 | LT-19-638 | 2026-11-19 | Y | Y | Scheduled | [6 empty] | Ready
NB-26-090 | 5CG4490759 | E1367 | Client Services | Wave 3 | LT-19-890 | 2026-11-19 | N | Y | Scheduled | [6 empty] | Not ready
NB-26-091 | 5CG4883366 | E1370 | Client Services | Wave 3 | LT-19-527 | 2026-11-19 | Y | N | Scheduled | [6 empty] | Not ready
NB-26-092 | 5CG5390383 | E1373 | Client Services | Wave 3 | LT-19-245 | 2026-11-19 | N | Y | Scheduled | [6 empty] | Not ready
NB-26-093 | 5CG6452831 | E1376 | Client Services | Wave 3 | LT-19-152 | 2026-11-20 | Y | N | Scheduled | [6 empty] | Not ready |  |  |  | Wave 3
NB-26-094 | 5CG6276714 | E1379 | Client Services | Wave 3 | LT-19-678 | 2026-11-20 | N | Y | Scheduled | [6 empty] | Not ready |  |  |  | Wave 3
NB-26-095 | 5CG2960518 | E1382 | Client Services | Wave 3 | LT-19-683 | 2026-11-20 | Y | N | Scheduled | [6 empty] | Not ready |  |  |  | Wave 3
NB-26-096 | 5CG7760581 | E1385 | Client Services | Wave 3 | LT-19-768 | 2026-11-20 | N | N | Scheduled | [6 empty] | Not ready |  |  |  | Wave 3

## Wave_Plan
Wave Plan & Go / No-Go Gate
A wave can start only when: the previous wave is 95%+ signed off, no Sev1 issue is open, and 95%+ of its users are ready (backup confirmed + MFA enrolled).
Wave | Who | Start | End | Laptops | Signed Off | % Done | Users Ready | % Ready | Open Sev1 (all waves) | Prior Wave % Done | Gate Check | Why
Wave 1 | Pilot: Finance & HR | 2026-10-19 | 2026-10-20 | 12 | 12 | 100% | 12 | 100% | 1 | n/a (pilot) | Complete | All laptops signed off
Wave 2 | Operations | 2026-10-26 | 2026-11-06 | 40 | 14 | 35% | 40 | 100% | 1 | 100% | In progress | Started Oct 26; 14 of 40 signed off
Wave 3 | Sales & Client Services | 2026-11-09 | 2026-11-20 | 44 | 0 | 0% | 18 | 40.91% | 1 | 35% | NO-GO | Prior wave 35% done (need 95%). 1 Sev1 issue open. Users ready 41% (need 95%).
The gate check is calculated for any wave that hasn't started yet. The go/no-go meeting is held 2 business days before each wave starts.
Formulas:
Start = IFERROR(INDEX(Device_Tracker!$G6:G160,MATCH([Wave],Device_Tracker!$T6:T160,0)),"")
End = IFERROR(INDEX(Device_Tracker!$G6:G160,MATCH([Wave],Device_Tracker!$U6:U160,0)),"")

## Issue_Log
Issue Log
Target = logged date + SLA (Sev1: 1 day, Sev2: 3 days, Sev3: 5 days). Open Sev1 issues block the next wave.
Yellow cells = you type or pick from a list here. White cells fill themselves in (don't type over them).
ID | Date Logged | Wave | Severity | Category | Description | Owner | Status | Resolved Date | Target Date | Days Open | SLA Flag | helper: open order
ISS-01 | 2026-10-19 | Wave 1 | Sev3 - Minor | Account / MFA | Two pilot users couldn't sign in to Teams until MFA was re-registered | IT Lead | Resolved | 2026-10-19 | 2026-10-24 | 0 | Met SLA
ISS-02 | 2026-10-20 | Wave 1 | Sev2 - Major | Peripheral | Older docking stations won't drive two monitors on the new laptops | Project Coordinator | Resolved | 2026-10-23 | 2026-10-23 | 3 | Met SLA
ISS-03 | 2026-10-27 | Wave 2 | Sev1 - Blocker | Application | Dispatch scheduling app won't activate its license on new laptops; 3 users kept on old laptops | Software Vendor | Open |  | 2026-10-28 | 3 | Overdue | 8
ISS-04 | 2026-10-28 | Wave 2 | Sev2 - Major | Hardware | One new laptop arrived with a dead screen; replacement ordered from the reseller | Project Coordinator | Open |  | 2026-10-31 | 2 | Open | 1009
ISS-05 | 2026-10-29 | Wave 2 | Sev3 - Minor | Data migration | OneDrive still syncing large folders at sign-off for 2 users | Deployment Technician | Resolved | 2026-10-30 | 2026-11-03 | 1 | Met SLA
Formulas:
Target Date = IF([Date Logged]="","",[Date Logged]+IF([Severity]="Sev1 - Blocker",1,IF([Severity]="Sev2 - Major",3,5)))

## Daily_Log
Daily Deployment Log — Plan vs. Actual
Planned = laptops scheduled that day. Actual = laptops signed off that day. Both come straight from the Device_Tracker.
[6 empty] | Status date: | 2026-10-30
Date | Planned | Actual (signed off) | Planned to Date | Actual to Date | Ahead / (Behind)
2026-10-19 | 6 | 6 | 6 | 6 | 0
2026-10-20 | 6 | 6 | 12 | 12 | 0
2026-10-21 | 0 | 0 | 12 | 12 | 0
2026-10-22 | 0 | 0 | 12 | 12 | 0
2026-10-23 | 0 | 0 | 12 | 12 | 0
2026-10-26 | 4 | 4 | 16 | 16 | 0
2026-10-27 | 4 | 1 | 20 | 17 | -3
2026-10-28 | 4 | 3 | 24 | 20 | -4
2026-10-29 | 4 | 4 | 28 | 24 | -4
2026-10-30 | 4 | 2 | 32 | 26 | -6
2026-11-02 | 4 | 0 | 36
2026-11-03 | 4 | 0 | 40
2026-11-04 | 4 | 0 | 44
2026-11-05 | 4 | 0 | 48
2026-11-06 | 4 | 0 | 52
2026-11-09 | 5 | 0 | 57
2026-11-10 | 5 | 0 | 62
2026-11-11 | 5 | 0 | 67
2026-11-12 | 5 | 0 | 72
2026-11-13 | 4 | 0 | 76
2026-11-16 | 4 | 0 | 80
2026-11-17 | 4 | 0 | 84
2026-11-18 | 4 | 0 | 88
2026-11-19 | 4 | 0 | 92
2026-11-20 | 4 | 0 | 96

## Comms_Plan
User Communication Plan (per wave)
Every user hears about their swap 3 times before it happens, so nobody is surprised and backups get done.
When | Message | Audience | Channel | Owner | Goal
5 business days before | "Your new laptop is coming": date, what to expect, 30-minute appointment | Wave users + managers | Email | Project Coordinator | No surprises
3 business days before | Reminder + backup checklist (save files to OneDrive, confirm MFA works on your phone) | Wave users | Email + Teams | Project Coordinator | Backup and MFA done before swap day
1 business day before | Appointment time and where to bring the old laptop | Each user | Teams message | Deployment Technician | Show up on time with the old laptop
Swap day | 30-minute swap: sign in, check files and apps, sign off | Each user | In person | Deployment Technician | User signs off that everything works
1 business day after | Two-question check-in: "Is everything working? Anything missing?" | Wave users | Teams poll | Project Coordinator | Catch problems early
5 business days after | Reminder to return the old laptop (if not returned) | Users flagged "Chase old laptop" | Email | Project Coordinator | Every old laptop wiped and recovered

## Lists
Lists
Drop-down values used across the workbook.
Device Status | Severity | Issue Category | Wave | Y/N | Issue Status | Department | Issue Owner
Scheduled | Sev1 - Blocker | Hardware | Wave 1 | Y | Open | Finance | IT Lead
Imaged | Sev2 - Major | Application | Wave 2 | N | Resolved | HR | Project Coordinator
Delivered | Sev3 - Minor | Account / MFA | Wave 3 |  |  | Operations | Deployment Technician
Data Migrated |  | Data migration |  |  |  | Sales | Software Vendor
Signed Off |  | Peripheral |  |  |  | Client Services | Reseller
Blocked | [6 empty] | Help Desk