## README
PMO Portfolio Report Workbook
Built by Adam J. Asifo (Claude by Anthropic assisted with formulas and testing) · adamjasifo@gmail.com
What this is
A small project management office (PMO) setup: 10 projects, one monthly update from each project manager, and one dashboard for leadership. It also checks the updates: it catches projects reported Green when the numbers say otherwise ('watermelons'), missing or late updates, and % complete that went backwards.
Why build it this way: I can work out any one of these numbers by hand. But 10 projects × 12 months is 120 updates a year, and every project should be judged by the same rules every month.
Start here: you only need these 3 things
Don't get overwhelmed. Most of this file fills itself in. These are the only places you type or pick something; everything else updates on its own.
Where | What you do | What happens
Portfolio_Dashboard → cell C4 (Month) | Pick a month from the drop-down. | The table, the counts and the flags all switch to that month.
Monthly_Updates → yellow columns | Add one row per project per month: pick the month and project ID, type % complete, cost to date, forecast cost and forecast finish, and pick the PM's color. | The white columns compare it to the plan and the rules, and flag watermelons, late updates and % that went backwards.
Rules → yellow cells | Optional: change a threshold, for example Red at −15 points. | Every project is re-judged by the new rule.
Yellow cells = you type or pick from a list. Cells with a small arrow have a drop-down menu: click the cell, then the arrow, and pick a word. White cells are formulas, so leave them alone.
What each tab is for
Portfolio_Dashboard | One page for leadership: every project's color (the PM's vs. the calculated one), flags, budget vs. forecast, a trend chart.
Monthly_Updates | 4 months of updates from 5 project managers, each checked against the plan.
Project_Register | The plan for each project: start, planned finish and budget. Everything is measured against this.
Resource_Load | Hours per person per month vs. capacity (140 hours). Over 100% = overbooked.
Rules | The Amber and Red thresholds, in one place, written in plain English.
Lists | The choices in every drop-down.
Try it (1 minute)
1. Go to the Portfolio_Dashboard and change cell C4 to September 2026.
2. P-201 (CRM Data Migration) is already flagged as a watermelon that month: the PM said Green, but it was 13 points behind plan.
3. Switch back to October 2026: it's now 24 points behind and Red.
To undo, press Ctrl+Z (Cmd+Z on a Mac).
Good to know
• Blank on purpose: P-208's October row has no numbers because the PM didn't send an update. That's why the dashboard shows 'Missing update'. Closed and on-hold projects show '—' because they aren't scored.
• Planned % is simple: 50 days into a 100-day project, you should be about 50% done. Schedule variance = reported % minus planned %, in points.
• Next month: add the new month to Lists → Report Month, then add the PMs' rows to Monthly_Updates. The formulas are already filled down.
• Works in Excel 2010 or newer (Windows or Mac), Excel online and Google Sheets. Formulas only, no macros, so no security warnings.
• All companies, people, dates and dollar amounts are fictional sample data.

## Portfolio_Dashboard
Portfolio Dashboard — 10 Projects, One Page
Sample PMO report with fictional data. Pick a month (yellow cell). Every number is calculated from the register and the monthly updates.
| Month: | 2026-10-31 |  | 202610
| Active projects |  | Green / Amber / Red (calculated) |  | Watermelons (PM says Green, data doesn't) |  | Updates missing / late
| 8 |  | 2 / 3 / 2 |  | 2 |  | 1 / 1
| Budget (active projects) |  | Forecast (active projects) |  | Slipping over 30 days |  | People overbooked (next 3 months)
| 674000 |  | 687000 |  | 1 |  | 2
Project status for the selected month
| ID | Project | PM | Reported % | Planned % | Sched. Var. (pts) | Cost vs Budget | Finish Slip (days) | PM's Color | Calculated Color | Flag
| P-201 | CRM Data Migration | D. Carter | 52% | 76% | -24 | 103.3% | 0 | Green | Red | Watermelon | Active | 186000
| P-202 | Warehouse Label Printer Rollout | S. Nguyen | 84% | 85.4% | -1 | 97.62% | 0 | Green | Green |  | Active | 41000
| P-203 | HR Onboarding Portal | D. Carter | 78% | 81.45% | -3 | 104.2% | 0 | Amber | Amber |  | Active | 99000
| P-204 | HQ Lobby Refresh | R. Patel | — | — | — | — | — | — | Closed |  | Closed | 60000
| P-205 | Fleet GPS Rollout | S. Nguyen | 80% | 100% | -20 | 105.3% | 45 | Red | Red |  | Active | 79000
| P-206 | SOC 2 Readiness | K. Brooks | 43% | 51.01% | -8 | 98.33% | 0 | Amber | Amber | Late update | Active | 118000
| P-207 | Website Redesign | L. Ortiz | 52% | 49.72% | 2 | 100% | 0 | Green | Green |  | Active | 70000
| P-208 | Phone System to Teams Calling | K. Brooks | — | 61.36% | — | — | — | — | No update | Missing update | Active | 38000
| P-209 | Records Digitization | R. Patel | 55% | 61.62% | -7 | 103.7% | 0 | Green | Amber | Watermelon · % dropped | Active | 56000
| P-210 | Parking Lot Resurfacing | L. Ortiz | 25% | — | — | 100% | — | Amber | On Hold |  | On Hold | 85000
Color trend (calculated)
| Month | Green | Amber | Red
| 2026-07-31 | 7 | 0 | 0
| 2026-08-31 | 7 | 2 | 0
| 2026-09-30 | 4 | 4 | 0
| 2026-10-31 | 2 | 3 | 2

## Monthly_Updates
Monthly Updates from Project Managers
PMs fill the yellow columns by the 5th of each month. The white columns check the update against the plan and the rules.
Yellow cells = you type or pick from a list here. White cells fill themselves in (don't type over them).
Month | Project ID | Project | Reported % Complete | Actual Cost to Date | Forecast Total Cost | Forecast Finish | PM's Color | PM Note | Date Submitted | Planned % (straight-line) | Schedule Variance (pts) | Cost Forecast vs Budget | Finish Slip (days) | Calculated Color | Watermelon? | Update Timing | % Dropped? | helper: key | Status This Month
2026-07-31 | P-201 | CRM Data Migration | 27% | 22000 | 180000 | 2026-12-18 | Green | Field mapping done | 2026-08-03 | 30% | -3 | 100% | 0 | Green |  | On time |  | P-201¦202607 | Active
2026-07-31 | P-202 | Warehouse Label Printer Rollout | 15% | 6000 | 42000 | 2026-11-20 | Green | Printers ordered | 2026-08-02 | 18.25% | -3 | 100% | 0 | Green |  | On time |  | P-202¦202607 | Active
2026-07-31 | P-203 | HR Onboarding Portal | 38% | 26000 | 95000 | 2026-12-11 | Green | Design approved | 2026-08-03 | 39.82% | -2 | 100% | 0 | Green |  | On time |  | P-203¦202607 | Active
2026-07-31 | P-204 | HQ Lobby Refresh | 80% | 41000 | 60000 | 2026-09-25 | Green | Furniture delivered | 2026-08-02 | 67.44% | 13 | 100% | 0 | Green |  | On time |  | P-204¦202607 | Active
2026-07-31 | P-205 | Fleet GPS Rollout | 15% | 9000 | 75000 | 2026-10-30 | Green | Units ordered | 2026-08-04 | 16.51% | -2 | 100% | 0 | Green |  | On time |  | P-205¦202607 | Active
2026-07-31 | P-206 | SOC 2 Readiness | 19% | 14000 | 120000 | 2027-03-26 | Green | Gap assessment done | 2026-08-04 | 20.13% | -1 | 100% | 0 | Green |  | On time |  | P-206¦202607 | Active
2026-07-31 | P-209 | Records Digitization | 12% | 5000 | 54000 | 2027-01-15 | Green | Scanning vendor selected | 2026-08-02 | 15.15% | -3 | 100% | 0 | Green |  | On time |  | P-209¦202607 | Active
2026-08-31 | P-201 | CRM Data Migration | 40% | 51000 | 180000 | 2026-12-18 | Green | Test load 1 complete | 2026-09-04 | 45.5% | -5 | 100% | 0 | Amber | Watermelon | On time |  | P-201¦202608 | Active
2026-08-31 | P-202 | Warehouse Label Printer Rollout | 38% | 15000 | 42000 | 2026-11-20 | Green | Pilot site live | 2026-09-03 | 40.88% | -3 | 100% | 0 | Green |  | On time |  | P-202¦202608 | Active
2026-08-31 | P-203 | HR Onboarding Portal | 52% | 42000 | 95000 | 2026-12-11 | Green | Build started | 2026-09-05 | 53.85% | -2 | 100% | 0 | Green |  | On time |  | P-203¦202608 | Active
2026-08-31 | P-204 | HQ Lobby Refresh | 95% | 55000 | 59000 | 2026-09-25 | Green | Punch list | 2026-09-02 | 85.47% | 10 | 98.33% | 0 | Green |  | On time |  | P-204¦202608 | Active
2026-08-31 | P-205 | Fleet GPS Rollout | 40% | 30000 | 76000 | 2026-10-30 | Amber | Install vendor short-staffed | 2026-09-03 | 44.95% | -5 | 101.3% | 0 | Amber |  | On time |  | P-205¦202608 | Active
2026-08-31 | P-206 | SOC 2 Readiness | 29% | 27000 | 120000 | 2027-03-26 | Green | Policies drafted | 2026-09-05 | 30.54% | -2 | 100% | 0 | Green |  | On time |  | P-206¦202608 | Active
2026-08-31 | P-207 | Website Redesign | 18% | 9000 | 70000 | 2027-01-29 | Green | Kickoff + sitemap | 2026-09-02 | 15.64% | 2 | 100% | 0 | Green |  | On time |  | P-207¦202608 | Active
2026-08-31 | P-209 | Records Digitization | 35% | 17000 | 54000 | 2027-01-15 | Green | Scanning underway | 2026-09-04 | 30.81% | 4 | 100% | 0 | Green |  | On time |  | P-209¦202608 | Active
2026-08-31 | P-210 | Parking Lot Resurfacing | 25% | 20000 | 85000 | 2026-11-13 | Green | Contractor selected; site prep done | 2026-09-03 | 27.45% | -2 | 100% | 0 | Green |  | On time |  | P-210¦202608 | Active
2026-09-30 | P-201 | CRM Data Migration | 48% | 84000 | 182000 | 2026-12-18 | Green | Data cleanup taking longer than planned | 2026-10-02 | 60.5% | -13 | 101.1% | 0 | Amber | Watermelon | On time |  | P-201¦202609 | Active
2026-09-30 | P-202 | Warehouse Label Printer Rollout | 62% | 26000 | 41000 | 2026-11-20 | Green | 3 of 5 sites live | 2026-10-01 | 62.77% | -1 | 97.62% | 0 | Green |  | On time |  | P-202¦202609 | Active
2026-09-30 | P-203 | HR Onboarding Portal | 65% | 61000 | 99000 | 2026-12-11 | Amber | Extra sign-on (SSO) work quoted | 2026-10-04 | 67.42% | -2 | 104.2% | 0 | Amber |  | On time |  | P-203¦202609 | Active
2026-09-30 | P-204 | HQ Lobby Refresh | 100% | 58500 | 58500 | 2026-09-25 | Green | Closed Sep 25 | 2026-10-01 | 100% | 0 | 97.5% | 0 | Complete |  | On time |  | P-204¦202609 | Closed
2026-09-30 | P-205 | Fleet GPS Rollout | 62% | 52000 | 78000 | 2026-11-20 | Red | Vendor delays; new date Nov 20 | 2026-10-02 | 72.48% | -10 | 104% | 21 | Amber |  | On time |  | P-205¦202609 | Active
2026-09-30 | P-206 | SOC 2 Readiness | 35% | 40000 | 118000 | 2027-03-26 | Amber | Evidence collection behind | 2026-10-03 | 40.6% | -6 | 98.33% | 0 | Amber |  | On time |  | P-206¦202609 | Active
2026-09-30 | P-207 | Website Redesign | 35% | 21000 | 70000 | 2027-01-29 | Green | Designs approved | 2026-10-03 | 32.4% | 3 | 100% | 0 | Green |  | On time |  | P-207¦202609 | Active
2026-09-30 | P-208 | Phone System to Teams Calling | 25% | 8000 | 38000 | 2026-12-04 | Green | Numbers ported for pilot | 2026-10-03 | 26.14% | -1 | 100% | 0 | Green |  | On time |  | P-208¦202609 | Active
2026-09-30 | P-209 | Records Digitization | 60% | 31000 | 54000 | 2027-01-15 | Green | Ahead of plan | 2026-10-03 | 45.96% | 14 | 100% | 0 | Green |  | On time |  | P-209¦202609 | Active
2026-09-30 | P-210 | Parking Lot Resurfacing | 25% | 20000 | 85000 | 2026-11-13 | Amber | Put on hold: budget freeze | 2026-10-02 |  |  | 100% |  | On Hold |  | On time |  | P-210¦202609 | On Hold
2026-10-31 | P-201 | CRM Data Migration | 52% | 120000 | 186000 | 2026-12-18 | Green | Still targeting Dec 18 go-live | 2026-11-04 | 76% | -24 | 103.3% | 0 | Red | Watermelon | On time |  | P-201¦202610 | Active
2026-10-31 | P-202 | Warehouse Label Printer Rollout | 84% | 34000 | 41000 | 2026-11-20 | Green | On track for Nov 20 | 2026-11-02 | 85.4% | -1 | 97.62% | 0 | Green |  | On time |  | P-202¦202610 | Active
2026-10-31 | P-203 | HR Onboarding Portal | 78% | 79000 | 99000 | 2026-12-11 | Amber | Cost 4% over; sponsor informed | 2026-11-03 | 81.45% | -3 | 104.2% | 0 | Amber |  | On time |  | P-203¦202610 | Active
2026-10-31 | P-205 | Fleet GPS Rollout | 80% | 66000 | 79000 | 2026-12-14 | Red | New date Dec 14; 14 trucks left | 2026-11-03 | 100% | -20 | 105.3% | 45 | Red |  | On time |  | P-205¦202610 | Active
2026-10-31 | P-206 | SOC 2 Readiness | 43% | 52000 | 118000 | 2027-03-26 | Amber | Auditor booked for March | 2026-11-09 | 51.01% | -8 | 98.33% | 0 | Amber |  | Late |  | P-206¦202610 | Active
2026-10-31 | P-207 | Website Redesign | 52% | 34000 | 70000 | 2027-01-29 | Green | Build 50% done | 2026-11-02 | 49.72% | 2 | 100% | 0 | Green |  | On time |  | P-207¦202610 | Active
2026-10-31 | P-208 | Phone System to Teams Calling | [5 empty] | (No update received. It was due by the 5th.) |  | 61.36% |  |  |  | No update |  | Missing |  | P-208¦202610 | Active
2026-10-31 | P-209 | Records Digitization | 55% | 34000 | 56000 | 2027-01-15 | Green | Found 2 more boxes of files; rescoped | 2026-11-04 | 61.62% | -7 | 103.7% | 0 | Amber | Watermelon | On time | Dropped | P-209¦202610 | Active
2026-10-31 | P-210 | Parking Lot Resurfacing | 25% | 20000 | 85000 | 2026-11-13 | Amber | Still on hold | 2026-11-02 |  |  | 100% |  | On Hold |  | On time |  | P-210¦202610 | On Hold

## Project_Register
Project Register
One row per project: the plan everything is measured against. Fictional company and people.
Yellow cells = you type or pick from a list here. White cells fill themselves in (don't type over them).
ID | Project | Type | Project Manager | Sponsor | Status | Start | Planned Finish | Budget
P-201 | CRM Data Migration | IT | D. Carter | VP Sales | Active | 2026-06-01 | 2026-12-18 | 180000
P-202 | Warehouse Label Printer Rollout | Operations | S. Nguyen | COO | Active | 2026-07-06 | 2026-11-20 | 42000
P-203 | HR Onboarding Portal | IT | D. Carter | HR Director | Active | 2026-05-04 | 2026-12-11 | 95000
P-204 | HQ Lobby Refresh | Facilities | R. Patel | COO | Closed | 2026-04-06 | 2026-09-25 | 60000
P-205 | Fleet GPS Rollout | Operations | S. Nguyen | COO | Active | 2026-07-13 | 2026-10-30 | 75000
P-206 | SOC 2 Readiness | Compliance | K. Brooks | CFO | Active | 2026-06-01 | 2027-03-26 | 120000
P-207 | Website Redesign | Marketing | L. Ortiz | CMO | Active | 2026-08-03 | 2027-01-29 | 70000
P-208 | Phone System to Teams Calling | IT | K. Brooks | CIO | Active | 2026-09-07 | 2026-12-04 | 38000
P-209 | Records Digitization | Operations | R. Patel | CFO | Active | 2026-07-01 | 2027-01-15 | 54000
P-210 | Parking Lot Resurfacing | Facilities | L. Ortiz | COO | On Hold | 2026-08-03 | 2026-11-13 | 85000

## Resource_Load
Resource Load — Who Is Booked Over Capacity?
List each person's hours per project per month (left). The grid adds them up against capacity. Over 100% = overbooked.
Yellow cells = you type or pick from a list here. White cells fill themselves in (don't type over them).
[5 empty] | Monthly capacity (hours per person) |  |  | 140
Person | Role | Project ID | Month | Hours |  | 2026-11-30 | 2026-12-31 | 2027-01-31
D. Carter | Project Manager | P-201 | 2026-11-30 | 80 | Person | Nov 2026 | Dec 2026 | Jan 2027 | Peak % | Over?
D. Carter | Project Manager | P-203 | 2026-11-30 | 52 | D. Carter | 94.29% | 78.57% | 14.29% | 94.29%
D. Carter | Project Manager | P-201 | 2026-12-31 | 70 | S. Nguyen | 92.86% | 42.86% | 21.43% | 92.86%
D. Carter | Project Manager | P-203 | 2026-12-31 | 40 | K. Brooks | 85.71% | 71.43% | 64.29% | 85.71%
D. Carter | Project Manager | P-201 | 2027-01-31 | 20 | R. Patel | 50% | 50% | 35.71% | 50%
S. Nguyen | Project Manager | P-202 | 2026-11-30 | 40 | L. Ortiz | 64.29% | 64.29% | 71.43% | 71.43%
S. Nguyen | Project Manager | P-205 | 2026-11-30 | 90 | A. Kim | 120% | 85.71% | 50% | 120% | Overbooked
S. Nguyen | Project Manager | P-205 | 2026-12-31 | 60 | T. Jones | 85.71% | 107.1% | 28.57% | 107.1% | Overbooked
S. Nguyen | Project Manager | P-209 | 2027-01-31 | 30 | M. Davis | 21.43% | 21.43% | 0% | 21.43%
K. Brooks | Project Manager | P-206 | 2026-11-30 | 60
K. Brooks | Project Manager | P-208 | 2026-11-30 | 60 | Green under 90% · amber 90–100% · red over 100%. Row 5 above the grid holds the month each column adds up.
K. Brooks | Project Manager | P-206 | 2026-12-31 | 60
K. Brooks | Project Manager | P-208 | 2026-12-31 | 40
K. Brooks | Project Manager | P-206 | 2027-01-31 | 90
R. Patel | Project Manager | P-209 | 2026-11-30 | 70
R. Patel | Project Manager | P-209 | 2026-12-31 | 70
R. Patel | Project Manager | P-209 | 2027-01-31 | 50
L. Ortiz | Project Manager | P-207 | 2026-11-30 | 90
L. Ortiz | Project Manager | P-207 | 2026-12-31 | 90
L. Ortiz | Project Manager | P-207 | 2027-01-31 | 100
A. Kim | Business Analyst | P-201 | 2026-11-30 | 90
A. Kim | Business Analyst | P-203 | 2026-11-30 | 40
A. Kim | Business Analyst | P-206 | 2026-11-30 | 38
A. Kim | Business Analyst | P-201 | 2026-12-31 | 80
A. Kim | Business Analyst | P-206 | 2026-12-31 | 40
A. Kim | Business Analyst | P-206 | 2027-01-31 | 70
T. Jones | IT Technician | P-208 | 2026-11-30 | 80
T. Jones | IT Technician | P-201 | 2026-11-30 | 40
T. Jones | IT Technician | P-208 | 2026-12-31 | 90
T. Jones | IT Technician | P-201 | 2026-12-31 | 60
T. Jones | IT Technician | P-203 | 2027-01-31 | 40
M. Davis | Facilities Coordinator | P-209 | 2026-11-30 | 30
M. Davis | Facilities Coordinator | P-209 | 2026-12-31 | 30
Note on K4: About 35 project hours a week after meetings, email and admin.

## Rules
Status Rules (the same rules for every project)
The calculated color comes from these numbers, not from how a project 'feels'. Change a threshold here and every project re-checks.
Yellow cells = you type or pick from a list here. White cells fill themselves in (don't type over them).
Rule | Amber at | Red at | Plain English
Schedule variance (points behind plan) | -5 | -15 | Actual % complete minus planned % complete. -15 means 15 points behind.
Cost forecast vs. budget | 100% | 110% | Forecast total cost ÷ budget. Over 100% is Amber; over 110% is Red.
Finish date slip (days) | 0 | 30 | Forecast finish minus planned finish. Any slip is Amber; more than 30 days is Red.
Update due (days after month end) | 5 |  | Monthly updates are due by the 5th. Later = 'Late update'.
Calculated color: Red if ANY Red rule is hit. Amber if any Amber rule is hit. Otherwise Green. Projects on hold or closed aren't colored.
Watermelon check: a project the PM reported as Green, but the numbers say Amber or Red (green outside, red inside).

## Lists
Lists
Drop-down values.
Project Type | Project Status | RAG | Report Month | People | Role | Sponsor
IT | Active | Green | 2026-07-31 | A. Kim | Project Manager | CFO
Operations | On Hold | Amber | 2026-08-31 | D. Carter | Business Analyst | CIO
Facilities | Closed | Red | 2026-09-30 | K. Brooks | IT Technician | CMO
Compliance |  |  | 2026-10-31 | L. Ortiz | Facilities Coordinator | COO
Marketing |  |  |  | M. Davis |  | HR Director
|  |  |  | R. Patel |  | VP Sales
S. Nguyen
T. Jones