## README
Project Control Workbook: Office Build-Out & Move
Built by Adam J. Asifo (Claude by Anthropic assisted with formulas and testing) · adamjasifo@gmail.com
What this is
One file that runs a sample office renovation and a 45-person move. It tracks the schedule, the budget, open questions, risks and to-dos, and it writes the weekly status report for you.
Why build it this way: I can do this math by hand for one task. With 31 tasks, 8 budget lines and 4 logs, it's easy to slip, so the rules are built in and the answer is the same every week.
Start here: you only need these 4 things
Don't get overwhelmed. Most of this file fills itself in. These are the only places you type or pick something; everything else updates on its own.
Where | What you do | What happens
Dashboard → cell C4 (Status date) | Type a date, for example 11/20/2026. | Every task status, the project color and every number re-check as of that day.
Schedule → column I (% Complete) | Type how far along a task is, for example 50%. | That task's status, its Gantt bar color, the phase summary and the Dashboard all update.
ChangeOrders → column H (Status) | Pick Pending, Approved or Rejected from the drop-down. | Approved costs move into the Budget tab and come out of the contingency cushion.
Status_Report | Nothing to type. Read it, or copy it into an email. | Every sentence is written from the numbers in the other tabs.
Yellow cells = you type or pick from a list. Cells with a small arrow have a drop-down menu: click the cell, then the arrow, and pick a word. White cells are formulas, so leave them alone.
What each tab is for
Dashboard | One page: overall color and why, key numbers, phase summary, upcoming milestones, top risks.
Status_Report | The Friday status email, written by formulas.
Schedule | 31 tasks in 6 phases: dates, % complete, status and a Gantt chart that colors itself.
Budget | 8 budget lines: baseline, approved change orders, actual spend and forecast.
ChangeOrders | Requests for extra money, and what was decided. Totals are in the box on the right.
RFI_Submittals | Questions sent to the architect and product approvals, with due dates and an Overdue flag.
RAID_Log | Risks, Assumptions, Issues and Decisions. Risks and issues get a 1–5 score.
Action_Items | To-dos from meetings, with owner, due date and status.
Lists | The choices in every drop-down. Add a word here and it shows up in the menus.
Try it (1 minute)
1. Go to the Dashboard and change cell C4 to 11/20/2026.
2. Nothing else was updated, so 11 tasks turn Late and the project turns Red.
3. Look at the 'Why this color?' box under the color. It shows exactly which rule was hit.
To undo, press Ctrl+Z (Cmd+Z on a Mac).
Good to know
• Blank on purpose: Probability and Impact for Assumption and Decision rows (only risks and issues are scored), Response Date for RFIs that haven't been answered yet, and empty Notes cells.
• To add a task, RFI, risk, change order or action, type on the next empty row. The formulas are already there (down to row 60).
• The two rules that matter most: a task is At Risk when it's more than 15 points behind where it should be, and Late when it's past its finish date and not done. The project color rules are written under the color on the Dashboard.
• Works in Excel 2010 or newer (Windows or Mac), Excel online and Google Sheets. Formulas only, no macros, so no security warnings.
• All companies, people, dates and dollar amounts are fictional sample data.

## Dashboard
Suite 300 Build-Out & Office Move — Project Dashboard
Sample project with fictional data. Everything on this page is calculated from the other tabs.
| Status date | 2026-10-16 |  | Project | Relocate a 45-person team into a renovated 6,000 sq ft suite (Columbia, MD) by Dec 14
| OVERALL HEALTH |  |  | % Complete (weighted) |  | Planned % by status date |  | Tasks late |  | Open high risks / issues
| Amber |  |  | 43.57% |  | 49.16% |  | 2 |  | 2
Red = 3+ late tasks, over budget overall, or 3+ open high risks. Amber = any late task, any budget line over, or any open high risk. Otherwise Green.
|  |  |  | Revised budget |  | Forecast at completion |  | Variance (+ under) |  | Contingency left
| Why this color? |  |  | 515000 |  | 502400 |  | 12600 |  | 12950
| Late tasks | 2
| Over budget? | No
| Budget lines over | 3 |  | Open / overdue RFIs |  | Pending change orders |  | Overdue actions |  | Days to move-in day
| Open high risks | 2 |  | 4 / 1 |  | 7850 |  | 2 |  | 59
Phase summary
| Phase |  | Tasks | % Complete | Start | Finish | Late | At Risk | Status
| 1 Initiation |  | 4 | 49.34% | 2026-08-31 | 2026-12-14 | 0 | 0 | On Track
| 2 Design & Permits |  | 4 | 100% | 2026-09-08 | 2026-10-13 | 0 | 0 | Complete
| 3 Construction |  | 9 | 6.25% | 2026-10-14 | 2026-12-08 | 0 | 0 | On Track
| 4 IT & Low-Voltage |  | 6 | 46.09% | 2026-09-21 | 2026-12-03 | 1 | 1 | Late
| 5 Furniture & Move |  | 6 | 37.93% | 2026-09-28 | 2026-12-16 | 1 | 1 | Late
| 6 Closeout |  | 2 | 0% | 2026-12-15 | 2026-12-23 | 0 | 0 | Not Started
| Milestones due in the next 60 days | [5 empty] | Top open risks & issues
| Milestone |  |  | Due |  |  | ID | Description |  |  | Score
| Rough-in inspections passed |  |  | 2026-11-06 |  |  | R-01 | ISP circuit lead time (45–60 days) may miss the move date |  |  | 20
| Network & AV testing sign-off |  |  | 2026-12-03 |  |  | I-01 | East-wing floor is out of level; needs leveling compound |  |  | 15
| Final inspection & certificate of occupancy |  |  | 2026-12-08 |  |  | I-02 | Moving company quote expired; re-bid required |  |  | 12
| Move weekend |  |  | 2026-12-14 |  |  | R-02 | Furniture lead times of 8–10 weeks |  |  | 12
| — | [5 empty] | R-04 | Inspection scheduling delays with the county |  |  | 8
Task status mix
| Status | Tasks
| Complete | 8
| On Track | 2
| At Risk | 2
| Late | 2
| Not Started | 17
Formulas:
Start = IFERROR(INDEX(Schedule!$E6:E60,MATCH([OVERALL HEALTH],Schedule!$AI6:AI60,0)),"")
Planned % by status date = IFERROR(INDEX(Schedule!$G6:G60,MATCH([OVERALL HEALTH],Schedule!$AJ6:AJ60,0)),"")
Note on C4: Change this date to re-run every status calculation. For live use, type =TODAY().

## Status_Report
Weekly Status Report — Suite 300 Build-Out & Move
Status date: October 16, 2026 ¦ Prepared by: Project Coordinator
Overall health | Amber
Summary | The project is 44% complete against a plan of 49%. 2 tasks are late and 2 are at risk. Forecast cost is $502,400 against a revised budget of $515,000 ($12,600 under). Move-in day is 59 days away.
Completed in the last 7 days
| ✓ Building permit submitted & approved | 2026-10-13
| ✓ Demolition | 2026-10-16
Late or at risk — needs attention
ISP circuit ordered & install date confirmed — Late (IT Lead)
Network & AV design — At Risk (IT Lead)
Furniture vendor selected & PO issued — Late (Project Coordinator)
Moving company contracted — At Risk (Project Coordinator)
Upcoming milestones (next 60 days)
| Rough-in inspections passed | 2026-11-06
| Network & AV testing sign-off | 2026-12-03
| Final inspection & certificate of occupancy | 2026-12-08
Top risks & issues
R-01: ISP circuit lead time (45–60 days) may miss the move date (score 20)
I-01: East-wing floor is out of level; needs leveling compound (score 15)
I-02: Moving company quote expired; re-bid required (score 12)
Decisions needed from sponsor
D-01: Approve CO-04 floor leveling ($4,750) from contingency? — Needed by Oct 20 to protect the drywall start
Overdue action items
| A2: Get a written install date from the ISP carrier — IT Lead | 2026-10-14
| A6: Follow up with architect on RFI-003 — Project Coordinator | 2026-10-15

## Schedule
Schedule & Gantt
Enter Start, Duration (workdays) and % Complete. Finish, Planned %, Status and the Gantt bars calculate automatically.
| Yellow cells = you type or pick from a list here. White cells fill themselves in (don't type over them). | [10 empty] | Status date: Oct 16, 2026 |  | 2026-10-16 |  | Gantt key: blue = scheduled · navy = milestone · amber = at risk · red = late · grey = complete · yellow column = status week
ID | Phase | Task | Owner | Start | Duration (workdays) | Finish | Milestone? | % Complete | Planned % (by status date) | Status | Days Late | Notes | helper: upcoming | helper: done this wk | helper: attention | 2026-08-31 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21
T01 | 1 Initiation | Kickoff meeting & charter sign-off | Project Manager | 2026-08-31 | 1 | 2026-08-31 | Y | 100% | 100% | Complete | 0 | [21 empty] | 1 Initiation
T02 | 1 Initiation | Requirements walk-through with department leads | Project Coordinator | 2026-09-01 | 3 | 2026-09-03 | N | 100% | 100% | Complete | 0 | Headcount, seating, storage, IT needs per team
T03 | 1 Initiation | Baseline schedule & budget approved | Project Manager | 2026-09-04 | 2 | 2026-09-07 | Y | 100% | 100% | Complete | 0
T04 | 1 Initiation | Staff communication plan (weekly updates) | Project Coordinator | 2026-09-08 | 70 | 2026-12-14 | N | 45% | 41.43% | On Track | 0 | Friday email + FAQ page | [21 empty] | 1 Initiation
T05 | 2 Design & Permits | Space plan & test fit | Architect | 2026-09-08 | 8 | 2026-09-17 | N | 100% | 100% | Complete | 0 | [21 empty] | 2 Design & Permits
T06 | 2 Design & Permits | Construction drawings issued | Architect | 2026-09-18 | 8 | 2026-09-29 | Y | 100% | 100% | Complete | 0
T07 | 2 Design & Permits | Landlord approval of plans | Facilities | 2026-09-30 | 5 | 2026-10-06 | N | 100% | 100% | Complete | 0
T08 | 2 Design & Permits | Building permit submitted & approved | General Contractor | 2026-09-30 | 10 | 2026-10-13 | Y | 100% | 100% | Complete | 0 |  |  | 2026-10-13 00:02 | [19 empty] | 2 Design & Permits
T09 | 3 Construction | Demolition | General Contractor | 2026-10-14 | 3 | 2026-10-16 | N | 100% | 100% | Complete | 0 | Started after permit; floor-leveling issue found (I-01) |  | 2026-10-16 00:02 | [18 empty] | 3 Construction
T10 | 3 Construction | Framing & new walls | General Contractor | 2026-10-19 | 8 | 2026-10-28 | N | 0% | 0% | Not Started | 0
T11 | 3 Construction | Electrical rough-in | General Contractor | 2026-10-26 | 7 | 2026-11-03 | N | 0% | 0% | Not Started | 0
T12 | 3 Construction | HVAC modifications | General Contractor | 2026-10-26 | 8 | 2026-11-04 | N | 0% | 0% | Not Started | 0
T13 | 3 Construction | Rough-in inspections passed | General Contractor | 2026-11-05 | 2 | 2026-11-06 | Y | 0% | 0% | Not Started | 0 |  | 2026-11-06 00:03
T14 | 3 Construction | Drywall, tape & finish | General Contractor | 2026-11-09 | 8 | 2026-11-18 | N | 0% | 0% | Not Started | 0
T15 | 3 Construction | Paint & ceilings | General Contractor | 2026-11-19 | 5 | 2026-11-25 | N | 0% | 0% | Not Started | 0
T16 | 3 Construction | Flooring | General Contractor | 2026-11-30 | 4 | 2026-12-03 | N | 0% | 0% | Not Started | 0
T17 | 3 Construction | Final inspection & certificate of occupancy | General Contractor | 2026-12-04 | 3 | 2026-12-08 | Y | 0% | 0% | Not Started | 0 | Must pass before move weekend | 2026-12-08 00:03 | [20 empty] | 3 Construction
T18 | 4 IT & Low-Voltage | ISP circuit ordered & install date confirmed | IT Lead | 2026-09-21 | 15 | 2026-10-09 | N | 60% | 100% | Late | 5 | Carrier has not confirmed a date (R-01) |  |  | 23 | [17 empty] | 4 IT & Low-Voltage
T19 | 4 IT & Low-Voltage | Network & AV design | IT Lead | 2026-10-05 | 10 | 2026-10-16 | N | 50% | 100% | At Risk | 0 |  |  |  | 24
T20 | 4 IT & Low-Voltage | Low-voltage cabling vendor awarded | Project Coordinator | 2026-10-07 | 8 | 2026-10-16 | N | 90% | 100% | On Track | 0
T21 | 4 IT & Low-Voltage | Data cabling rough-in | Cabling Vendor | 2026-10-26 | 6 | 2026-11-02 | N | 0% | 0% | Not Started | 0
T22 | 4 IT & Low-Voltage | Switches, Wi-Fi APs & firewall installed | IT Lead | 2026-11-23 | 4 | 2026-11-26 | N | 0% | 0% | Not Started | 0
T23 | 4 IT & Low-Voltage | Network & AV testing sign-off | IT Lead | 2026-12-01 | 3 | 2026-12-03 | Y | 0% | 0% | Not Started | 0 |  | 2026-12-03 00:04 | [20 empty] | 4 IT & Low-Voltage
T24 | 5 Furniture & Move | Furniture vendor selected & PO issued | Project Coordinator | 2026-09-28 | 10 | 2026-10-09 | N | 80% | 100% | Late | 5 | Quotes 4% over budget; awaiting approval |  |  | 29 | [17 empty] | 5 Furniture & Move
T25 | 5 Furniture & Move | Moving company contracted | Project Coordinator | 2026-10-12 | 5 | 2026-10-16 | N | 60% | 100% | At Risk | 0 | First quote expired; re-bidding (I-02) |  |  | 30
T26 | 5 Furniture & Move | Label plan & staff packing guide distributed | Project Coordinator | 2026-11-30 | 5 | 2026-12-04 | N | 0% | 0% | Not Started | 0
T27 | 5 Furniture & Move | Furniture delivery & install | Furniture Vendor | 2026-12-03 | 4 | 2026-12-08 | N | 0% | 0% | Not Started | 0
T28 | 5 Furniture & Move | Move weekend | Mover | 2026-12-11 | 2 | 2026-12-14 | Y | 0% | 0% | Not Started | 0 | Fri evening pack-out, Mon day one | 2026-12-14 00:05
T29 | 5 Furniture & Move | Day-one support desk (hypercare) | IT Lead | 2026-12-14 | 3 | 2026-12-16 | N | 0% | 0% | Not Started | 0 | [22 empty] | 5 Furniture & Move
T30 | 6 Closeout | Punch list walkthrough & completion | Project Coordinator | 2026-12-15 | 5 | 2026-12-21 | N | 0% | 0% | Not Started | 0 | [21 empty] | 6 Closeout
T31 | 6 Closeout | Lessons learned & closeout report | Project Coordinator | 2026-12-21 | 3 | 2026-12-23 | Y | 0% | 0% | Not Started | 0 | [22 empty] | 6 Closeout
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Budget
Budget Tracker
Approved change orders are added to their category and drawn from contingency, so the total budget holds unless contingency runs out.
Yellow cells = you type or pick from a list here. White cells fill themselves in (don't type over them).
Category | Baseline Budget | Approved Change Orders | Revised Budget | Committed (POs/contracts) | Actual Spent to Date | Estimate to Complete | Forecast at Completion | Variance (+ under / − over) | % Spent | Status
Design & Permits | 38000 | 0 | 38000 | 36500 | 34200 | 2300 | 36500 | 1500 | 90% | Watch
Construction | 265000 | 6800 | 271800 | 262000 | 58000 | 214550 | 272550 | -750 | 21.34% | Over
Electrical & Data Cabling | 42000 | 2400 | 44400 | 41900 | 0 | 41900 | 41900 | 2500 | 0% | OK
IT Equipment | 36000 | 0 | 36000 | 12400 | 4100 | 30500 | 34600 | 1400 | 11.39% | Watch
AV & Conference Rooms | 18000 | 0 | 18000 | 0 | 0 | 18000 | 18000 | 0 | 0% | Watch
Furniture | 72000 | 0 | 72000 | 0 | 0 | 74800 | 74800 | -2800 | 0% | Over
Moving & Logistics | 14000 | 0 | 14000 | 0 | 0 | 16200 | 16200 | -2200 | 0% | Over
Contingency | 30000 | -9200 | 20800 | 0 | 0 | 7850 | 7850 | 12950 | 0% | OK
TOTAL | 515000 | 0 | 515000 | 352800 | 96300 | 406100 | 502400 | 12600 | 18.7% | Watch
Note on G13: Contingency forecast = value of change orders still pending approval.

## ChangeOrders
Change Order Log
Approved amounts flow into the Budget tab automatically.
Yellow cells = you type or pick from a list here. White cells fill themselves in (don't type over them).
CO # | Description | Requested By | Budget Category | Cost Impact ($) | Schedule Impact (days) | Date Submitted | Status | Decision Notes | Totals
CO-01 | Relocate 2 data drops after furniture layout change | Project Coordinator | Electrical & Data Cabling | 2400 | 0 | 2026-10-02 | Approved | Cheaper than moving desks | Approved | 9200
CO-02 | Add fire-rated wall at server room (plan review comment) | Architect | Construction | 6800 | 3 | 2026-09-29 | Approved | Code requirement | Pending | 7850
CO-03 | Upgrade main conference display to 86 inch | IT Lead | AV & Conference Rooms | 3100 | 0 | 2026-10-09 | Pending | Awaiting sponsor decision | Rejected | 2900
CO-04 | Floor leveling in east wing (found during demo) | General Contractor | Construction | 4750 | 2 | 2026-10-15 | Pending | Decision D-01
CO-05 | Add 4 sit-stand desks | Facilities | Furniture | 2900 | 0 | 2026-10-06 | Rejected | Defer to 2027 budget

## RFI_Submittals
RFI & Submittal Log
Due date = sent date + response window (workdays). Status flips to Overdue automatically.
Yellow cells = you type or pick from a list here. White cells fill themselves in (don't type over them).
Log # | Type | Subject | Sent To | Date Sent | Response Window (workdays) | Due Date | Response Date | Status | Days Outstanding | Notes
RFI-001 | RFI | Confirm ceiling height at server room for cable tray | Architect | 2026-09-22 | 5 | 2026-09-29 | 2026-09-25 | Answered | 3
RFI-002 | RFI | Fire-rated wall assembly detail | Architect | 2026-09-28 | 5 | 2026-10-05 | 2026-10-01 | Answered | 3 | Led to CO-02
RFI-003 | RFI | Existing floor box locations vs new desk layout | Architect | 2026-10-08 | 3 | 2026-10-13 |  | Overdue | 6 | Follow-up sent (action A6)
RFI-004 | RFI | HVAC diffuser relocation in conference room | General Contractor | 2026-10-14 | 5 | 2026-10-21 |  | Open | 2
SUB-001 | Submittal | Carpet tile product data & samples | Architect | 2026-10-05 | 10 | 2026-10-19 | 2026-10-13 | Answered | 6 | Approved as submitted
SUB-002 | Submittal | Door hardware schedule | Architect | 2026-10-09 | 10 | 2026-10-23 |  | Open | 5
SUB-003 | Submittal | Cable tray & Cat6A spec sheets | IT Lead | 2026-10-12 | 10 | 2026-10-26 |  | Open | 4
Formulas:
Due Date = IF([Date Sent]="","",WORKDAY([Date Sent],[Response Window (workdays)]))
Days Outstanding = IF([Date Sent]="","",IF([Response Date]<>"",NETWORKDAYS([Date Sent],[Response Date])-1,NETWORKDAYS([Date Sent],AsOf)-1))

## RAID_Log
RAID Log — Risks, Assumptions, Issues, Decisions
Score = Probability × Impact (1–5 each). 15+ = High, 8–14 = Medium, below 8 = Low.
Yellow cells = you type or pick from a list here. White cells fill themselves in (don't type over them).
ID | Type | Description | Category | Probability (1-5) | Impact (1-5) | Score | Rating | Owner | Date Raised | Status | Response / Mitigation | Days Open | helper: top risk | helper: open decision
R-01 | Risk | ISP circuit lead time (45–60 days) may miss the move date | Schedule | 4 | 5 | 20 | High | IT Lead | 2026-09-21 | Open | Escalate with carrier weekly; order LTE backup router as a bridge | 25 | 20.006
R-02 | Risk | Furniture lead times of 8–10 weeks | Schedule | 3 | 4 | 12 | Medium | Project Coordinator | 2026-09-28 | Open | Choose in-stock lines; lock ship date in the PO | 18 | 12.007
R-03 | Risk | Hidden conditions behind walls during demo | Cost | 3 | 3 | 9 | Medium | General Contractor | 2026-09-08 | Closed | Occurred — converted to issue I-01
R-04 | Risk | Inspection scheduling delays with the county | Schedule | 2 | 4 | 8 | Medium | General Contractor | 2026-09-30 | Monitoring | Book inspections 5 days ahead | 16 | 8.009
R-05 | Risk | Staff disruption during move weekend | People | 2 | 3 | 6 | Low | Project Coordinator | 2026-10-01 | Open | Packing guide, labels, day-one help desk | 15 | 6.01
I-01 | Issue | East-wing floor is out of level; needs leveling compound | Cost | 5 | 3 | 15 | High | General Contractor | 2026-10-15 | Open | CO-04 submitted; decision D-01 needed | 1 | 15.011
I-02 | Issue | Moving company quote expired; re-bid required | Schedule | 4 | 3 | 12 | Medium | Project Coordinator | 2026-10-12 | Open | 3 new quotes requested (action A3) | 4 | 12.012
A-01 | Assumption | Landlord provides after-hours elevator access for the move | Logistics |  |  |  | n/a | Facilities | 2026-09-04 | Open | Confirm in writing (action A5) | 42
D-01 | Decision | Approve CO-04 floor leveling ($4,750) from contingency? | Cost |  |  |  | n/a | Project Manager | 2026-10-15 | Open | Needed by Oct 20 to protect the drywall start | 1 |  | 14
D-02 | Decision | Keep existing phone system vs. move to cloud voice | IT |  |  |  | n/a | IT Lead | 2026-09-10 | Closed | Keep existing; revisit in 2027

## Action_Items
Meeting Action Items
Anything past due and not Done is flagged OVERDUE and shows on the status report.
Yellow cells = you type or pick from a list here. White cells fill themselves in (don't type over them).
# | Date Raised | Meeting | Action | Owner | Due | Status | Flag | helper: overdue
A1 | 2026-10-05 | Weekly OAC meeting | Send revised furniture layout to cabling vendor | Project Coordinator | 2026-10-07 | Done
A2 | 2026-10-12 | Weekly OAC meeting | Get a written install date from the ISP carrier | IT Lead | 2026-10-14 | Open | OVERDUE | 7
A3 | 2026-10-12 | Weekly OAC meeting | Re-bid moving company (3 quotes) | Project Coordinator | 2026-10-19 | Open | Due soon
A4 | 2026-10-15 | Site walk with GC | Price floor-leveling options for the east wing | General Contractor | 2026-10-16 | Done
A5 | 2026-10-14 | Landlord check-in | Confirm after-hours elevator reservation | Facilities | 2026-10-23 | Open
A6 | 2026-10-14 | Design coordination | Follow up with architect on RFI-003 | Project Coordinator | 2026-10-15 | Open | OVERDUE | 11

## Lists
Lists
Drop-down values used across the workbook. Add a row here and it shows up in the menus.
Phases | Owners | RAID Type | RAID Status | CO Status | Action Status | Yes/No | Log Type | Budget Categories | RAID Category | Meetings
1 Initiation | Project Manager | Risk | Open | Pending | Open | Y | RFI | Design & Permits | Schedule | Weekly OAC meeting
2 Design & Permits | Project Coordinator | Issue | Monitoring | Approved | Done | N | Submittal | Construction | Cost | Design coordination
3 Construction | Architect | Assumption | Closed | Rejected |  |  |  | Electrical & Data Cabling | IT | Site walk with GC
4 IT & Low-Voltage | General Contractor | Decision | [5 empty] | IT Equipment | Logistics | Landlord check-in
5 Furniture & Move | IT Lead | [6 empty] | AV & Conference Rooms | People
6 Closeout | Facilities | [6 empty] | Furniture | Quality
| Cabling Vendor | [6 empty] | Moving & Logistics
| Furniture Vendor | [6 empty] | Contingency
Mover
Finance